## Sheet1
Project Name/Location | Population Management Unit | State | Land Manager | Responsible Party | Treatment Type | Partners | Action Type | Action Type | Action Type | Total Acres | Total Miles | Total Sites | Primary Risk Addressed (from 2004 Lincoln County Plan) | Secondary Risk Addressed (from 2004 Lincoln County Plan) | Factor A: Habitat (from FWS 2010 finding) Y/N | Factor B: Overuse (from FWS 2010 finding) Y/N | Factor C: Disease Predation (from FWS 2010 finding) Y/N | Factor D: Regulatory (from FWS 2010 finding) Y/N | Factor E: Other (from FWS 2010 finding) Y/N | Date Started or Planned Start Date | Date Completed | Project Status | Funded Y/N | Monitoring Y/N | Comments
21 Mile Seeding (550766) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 3342 | [11 empty] | Completed |  |  | Historic Seeding
Boren Chaining and Seeding (550518) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 1275 | [10 empty] | 1964 | Completed |  |  | Historic Seeding
Brown Springs Veg. Conversion (554616) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 520 | [11 empty] | Completed |  |  | Historic Seeding
Burnt canyon Chaining/Seeding (554330/554331) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 1993 | [11 empty] | Completed |  |  | Historic Seeding
Burnt Canyon Seeding (554256) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 627 | [11 empty] | Completed |  |  | Historic Seeding
Cave Valley Ranch Aerial Seeding (550641) | Cave | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 965 | [11 empty] | Completed |  |  | Historic Seeding
Cave Valley Seeding (550799) | Cave | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 3089 | [11 empty] | Completed |  |  | Historic Seeding
Cottonwood Seeding (550745) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 2289 | [11 empty] | Completed |  |  | Historic Seeding
Crawcreek Seeding (550608) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 3739 | [11 empty] | Completed |  |  | Historic Seeding
Deer Flat Seeding (550004) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 1030 | [11 empty] | Completed |  |  | Historic Seeding
Dle Chaining and Seeding (551080) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 1198 | [10 empty] | 1969 | Completed |  |  | Historic Seeding
Dutch John Seeding #2 (550918) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 2203 | [10 empty] | 1966 | Completed |  |  | Historic Seeding
Dutch John Seeding (550624) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 1740 | [10 empty] | 1964 | Completed |  |  | Historic Seeding
Freestone Seeding (55076) | Cave | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 1086 | [11 empty] | Completed |  |  | Historic Seeding
Geyser Chaining and Seeding (551082) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 810 | [10 empty] | 1969 | Completed |  |  | Historic Seeding
Gouge Eye Seeding (551053) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 5689 | [10 empty] | 1968 | Completed |  |  | Historic Seeding
Highway Seeding (550613) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 3153 | [10 empty] | 1967 | Completed |  |  | Historic Seeding
Highway Seeding Extension (554039) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 715 | [10 empty] | 1969 | Completed |  |  | Historic Seeding
Horsethief Chaining and Seeding | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 742 | [11 empty] | Completed
Hulse Canyon Seeding (550605) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 5059 | [11 empty] | Completed |  |  | Historic Seeding
Kirkeby Seeding (550620) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 1631 | [11 empty] | Completed |  |  | Historic Seeding
Meadow Valley Seeding (550133) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 3333 | [11 empty] | Completed |  |  | Historic Seeding
Milk Ranche Chaining/Seeding Ext. (550914) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 1183 | [10 empty] | 1966 | Completed |  |  | Historic Seeding
Milk Well Seeding (550422) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 4501 | [10 empty] | 1965 | Completed |  |  | Historic Seeding
Mt. Wilson Seeding (550560) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 7427 | [11 empty] | Completed |  |  | Historic Seeding
Mustang Seeding (551078) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 6313 | [10 empty] | 1969 | Completed |  |  | Historic Seeding
Patterson Pass Seeding (550631) | Cave | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 982 | [11 empty] | Completed |  |  | Historic Seeding
Pony Springs Study Plot (550149) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 857 | [11 empty] | Completed |  |  | Historic Seeding
Shaffer Seeding (550152) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 1181 | [10 empty] | 1964 | Completed |  |  | Historic Seeding
Sheep Trail Seeding (550430) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 705 | [11 empty] | Completed |  |  | Historic Seeding
Travis Seeding (550499) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 11329 | [10 empty] | 1967 | Completed |  |  | Historic Seeding
Twisselman Seeding (554235) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 853 | [10 empty] | 1976 | Completed |  |  | Historic Seeding
Upper Cottonwood Seeding (550139) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 435 | [11 empty] | Completed |  |  | Historic Seeding
White Rock Seeding Addition (550649) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 1313 | [11 empty] | Completed |  |  | Historic Seeding
White Rock Wash Seeding (550395) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 4130 | [11 empty] | Completed |  |  | Historic Seeding
Willow Wash Seeding (550966) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 1064 | [11 empty] | Completed |  |  | Historic Seeding
Wilson seeding (554302) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 792 | [11 empty] | Completed |  |  | Historic Seeding
Witts Seeding (551054) | Lincoln | NV | BLM - Ely Field Office |  | AGCR Seeding | BLM | Treatment - Seeding |  |  | 2840 | [11 empty] | Completed |  |  | Historic Seeding
Cactus Fire Rehab/Muleshoe Valley | Cave | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation | Treatment - Seeding |  | 416 |  |  | Wildfire | Invasive Species - Other | Yes | No | No | No | No | 2007-02-12 | 2007-02-12 | Completed | Yes | Unknown
Coyote Fire Rehab | Lincoln | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 10179 | [11 empty] | Completed
Delmue Fire Rehab Seeding | Lincoln | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 8113 | [11 empty] | Completed
Dutch John Fire | Lincoln | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 441 | [11 empty] | Completed
Eagle Fire | Lincoln | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 7923 | [11 empty] | Completed
Flatnose RX Burn/East of Echo Canyon Park | Lincoln | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Prescribed |  |  | 3569 |  |  | Invasive Species - Conifer Encroachment | Wildfire | Yes | No | No | No | No | 2004-08-01 | 2004-09-01 | Completed | Yes | No
Kicksmiller Fire | Cave | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 2456 | [10 empty] | 2007-02-15 | Completed
King Fire | Cave | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 210 | [10 empty] | 2007-03-04 | Completed
Muleshoe Fire | Cave | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 203 | [10 empty] | 2007-02-12 | Completed
Parsnip Fire | Lincoln | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 2052 | [11 empty] | Completed
Peers Fire | Cave/Lincoln | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 870 | [10 empty] | 2007-02-12 | Completed
Pioche 1 | Lincoln | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 336 | [11 empty] | Completed
Silverhorn Fire | Cave/Lincoln | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 383 | [11 empty] | Completed
Stampede | Lincoln | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 151 | [11 empty] | Completed
Weepah Fire | Cave | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 61 | [10 empty] | 2007-03-04 | Completed
Whipple Fire | Quinn | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 320 | [10 empty] | 2007-03-04 | Completed
White Rock Fire Rehab | Lincoln | NV | BLM - Ely Field Office |  | ES&R | BLM | Fire Rehabilitation |  |  | 3015 | [10 empty] | 2013 | Completed |  |  | Forb/grass/shrub seeding, herbicide treatment, soil stabilization
Cave Valley Mow & Seed/Cave Valley | Cave | NV | BLM - Ely Field Office |  | Treatment - Chemical | BLM | Treatment - Sagebrush Mowing | Treatment - Seeding |  | 969 |  |  | Sagebrush Habitat Condition | Invasive Species - Other | Yes | No | No | No | No | 2008-11-15 | 2009-01-31 | Completed | Yes | Yes
Cave Valley Ranch Rabbitbrush Treatment/Cave Valley Ranch | Cave | NV | BLM - Ely Field Office |  | Treatment - Chemical | BLM/Permittee/RMEF | Treatment - Chemical | Treatment - Sagebrush Drill Seeding |  | 840 |  |  | Invasive Species - Other | Riparian/Meadow Quality | Yes | No | No | No | No | 2009-08-28 | 2010-11-15 | Completed | Yes | Yes | Rabbitbrush mowing
Hamblin Valley Spike Treatment--Hamblin Valley | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Chemical | BLM | Treatment - Chemical |  |  | 778 |  |  | Sagebrush Habitat Condition |  | Yes | No | No | No | No | 2009-10-15 | 2009-11-30 | Completed | Yes | Yes
Tub Peak Spike Treatment/Atlanta Area-Lake Valley | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Chemical | BLM | Treatment - Chemical |  |  | 1927 |  |  | Sagebrush Habitat Condition |  | Yes | No | No | No | No | 2009-10-15 | 2009-10-16 | Completed | Yes | Yes
Burnt Canyon Chaining Maintenance/Mt. Wilson Area-East Camp Valley | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Lop & Scatter |  |  | 1604 |  |  | Invasive Species - Conifer Encroachment | Sagebrush Habitat Condition | Yes | No | No | No | No | 2011-08-01 | 2012-07-12 | Completed | Yes | No
Caselton Chaining/Pioche-Caselton | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Chaining | Treatment - Seeding |  | 1083 |  |  | Invasive Species - Conifer Encroachment | Wildfire | Yes | no | No | No | No | 2010-11-20 | 2010-12-15 | Completed | Yes | Yes
Cave Valley Roller Chop/Cave Valley | Cave | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Mechanical | Treatment - Seeding |  | 861 |  |  | Sagebrush Habitat Condition | Invasive Species - Other | Yes | No | No | No | No | 2009-09-01 | 2009-11-15 | Completed | Yes | Yes
Condor Canyon Aereal Seeding | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Seeding |  |  | 1338 | [10 empty] | 2013-09-30 | Completed
Eagle Valley/Ursine | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mastication |  |  | 345 |  |  | Invasive Species - Conifer Encroachment | Wildfire | Yes | No | No | No |  | 2008-09-02 | 2008-10-18 | Completed | Yes | Yes
Hamblin Valley Chaining/Hamblin Valley | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Sagebrush Chaining | Treatment - Seeding |  | 1340 |  |  | Sagebrush Habitat Condition | Invasive Species - Other | Yes | No | No | No | No | 2008-11-01 | 2009-01-15 | Completed | Yes | Yes
Patterson Wash Mow & Seed/Patterson Wash | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Sagebrush Mowing | Treatment - Seeding |  | 441 |  |  | Sagebrush Habitat Condition | Invasive Species - Other | Yes | No | No | No | No | 2009-07-20 | 2009-12-20 | Completed | Yes | Yes
Patterson Wash Roller Chop & Seed/Patterson Wash | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Sagebrush Roller Chopper | Treatment - Seeding |  | 907 |  |  | Sagebrush Habitat Condition | Invasive Species - Other | Yes | No | No | No | No | 2009-09-15 | 2009-10-15 | Completed | Yes | Yes
Pioche WUI Mow and Seed/Pioche | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Sagebrush Mowing | Treatment - Seeding |  | 1059 |  |  | Wildfire | Sagebrush Habitat Condition | Yes | No | No | No | No | 2010-10-12 | 2011-09-17 | Completed | Yes | Yes
Reeds Cabin Chaining Maintenance/East Spring Valley | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer removal |  |  | 576 |  |  | Invasive Species - Conifer Encroachment | Sagebrush Habitat Condition | Yes | No | No | No | No | 2012-06-05 | 2012-07-12 | Completed | Yes | No
Reeds Cabin Chaining North (554701) | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Chaining | Treatment - Seeding |  | 171 | [11 empty] | Completed |  |  | Historic
Reeds Cabin Chaining South (554701) | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Chaining | Treatment - Seeding |  | 405 | [11 empty] | Completed |  |  | Historic
Rice Cemetery Mowing/Spring Valley State Park Area | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Sagebrush Mowing |  |  | 214 |  |  | Wildfire | Sagebrush Habitat Condition | Yes | No | No | No | No | 2009-08-01 | 2009-08-27 | Completed | Yes | Yes
South Spring Valley Anchor Chain/South Spring Valley | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Mechanical | Treatment - Seeding |  | 3104 |  |  | Invasive Species - Conifer Encroachment | Wildfire | Yes | No | No | No | No | 2009-01-15 | 2009-03-15 | Completed | Yes | Yes
South Spring Valley Mow & Seed/South Spring Valley | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Sagebrush Mowing | Treatment - Sagebrush Drill Seeding |  | 625 |  |  | Sagebrush Habitat Condition | Invasive Species - Other | Yes | No | No | No | No | 2009-10-10 | 2009-11-30 | Completed | Yes | Yes
South Spring Valley Roller Chop & Seed/South Spring Valley | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Sagebrush Roller Chopper | Treatment - Seeding |  | 720 |  |  | Sagebrush Habitat Condition | Invasive Species - Other | Yes | No | No | No | No | 2009-09-15 | 2009-11-15 | Completed | Yes | Yes
South Spring Valley Smooth Chain/South Spring Valley | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Mechanical | Treatment - Seeding |  | 878 |  |  | Sagebrush Habitat Condition | Invasive Species - Other | Yes | No | No | No | No | 2008-11-01 | 2009-01-15 | Completed | Yes | Yes
Tub Peak Hills #1 Lek Enhancement | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | NDOW | Treatment - Conifer Handcutting |  |  | 238 |  |  | Invasive Species - Conifer Encroachment |  | Yes | [6 empty] | Completed
Tub Peak Hills #3 Lek Enhancement | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | NDOW | Treatment - Conifer Handcutting |  |  | 56 |  |  | Invasive Species - Conifer Encroachment |  | Yes | [6 empty] | Completed
Tub Pek Hills #2 Lek Enhancement | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | NDOW | Treatment - Conifer Handcutting |  |  | 56 |  |  | Invasive Species - Conifer Encroachment |  | Yes | [6 empty] | Completed
West Hamlin Road Lek Enhancement | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | NDOW | Treatment - Conifer Handcutting |  |  | 397 |  |  | Invasive Species - Conifer Encroachment |  | Yes | [6 empty] | Completed
Whittemore/Little Spring Valley #1 Lek Enhancement | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | NDOW | Treatment - Conifer Handcutting |  |  | 161 |  |  | Invasive Species - Conifer Encroachment |  | Yes | [6 empty] | Completed
Woods_McCollough Chaining | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Chaining |  |  | 1046 | [11 empty] | Completed
Woods-McCullough Chaining Maintenance/West Hamblin Valley | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Handcutting |  |  | 1045 |  |  | Invasive Species - Conifer Encroachment | Sagebrush Habitat Condition | Yes | No | No | No | No | 2011-04-05 | 2012-02-15 | Completed | Yes | Yes
Caselton Powerline Thinning | Lincoln | NV | BLM - Ely Field Office |  | WUI | BLM | Treatment - Conifer Handcutting |  |  | 136 | [10 empty] | 2012-04-15 | Completed
Mt. Wilson WUI | Lincoln | NV | BLM - Ely Field Office |  | WUI | BLM | Treatment - Conifer Handcutting |  |  | 743 | [11 empty] | Completed
Mt. Wilson WUI/Lake Valley--West of Mt. Wilson Guest Ranch | Lincoln | NV | BLM - Ely Field Office |  | WUI | BLM | Treatment - Conifer removal | Treatment - Seeding |  | 743 |  |  | Invasive Species - Conifer Encroachment | Wildfire | Yes | No | No | No | No | 2003-07-01 | 2003-12-15 | Completed | Yes | Yes
Stewart Ranch-Kixmiller WUI/KixMiller Summit | Lincoln | NV | BLM - Ely Field Office |  | WUI | BLM | Treatment - Conifer Mastication | Treatment - Seeding |  | 483 |  |  | Invasive Species - Conifer Encroachment | Wildfire | Yes | No | No | No | No | 2007-11-27 | 2009-03-11 | Completed | Yes | No
Winz Creek WUI/Near Atlanta Farms--Lake Valley | Lincoln | NV | BLM - Ely Field Office |  | WUI | BLM | Treatment - Conifer Mastication |  |  | 551 |  |  | Invasive Species - Conifer Encroachment | Wildfire | Yes | No | No | No | No | 2008-07-31 | 2008-12-05 | Completed | Yes | Yes
Winz Creek Wildlife Corridor | Lincoln | NV | Private |  | Treatment - Physical | NDOW, NDF, CD, MVWU |  |  |  | 90 | [11 empty] | Ongoing Action
Browns Spring | Lincoln | NV | Private |  | Treatment - Physical | CD, NDF |  |  |  | 35 | [11 empty] | Ongoing Action
Meloy WUI/Near Malloy Spring | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer removal | Treatment - Seeding |  | 289 |  |  | Wildfire | Invasive Species - Conifer Encroachment | Yes | No | No | No | No | 2009-10-01 | 2010-03-25
Patterson Pass Sage Grouse Habitat Imprvement Project | Cave | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM, NDOW, County Game Board, MVWU, Mule Deer Found. | Treatment - Conifer Lop & Scatter | Treatment - Conifer Chaining |  | 6810 |  |  | Invasive Species - Conifer Encroachment | Invasive Species - Conifer Encroachment | [5 empty] | 2013-07-15 | 2015-09-30 | Completed |  |  | 5,860 acres lop and scatter, 950 acres chaining
Gouge Eye Sage Grouse Habitat Improvement Project | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Lop & Scatter |  |  | 830 |  |  | Invasive Species - Conifer Encroachment | Invasive Species - Conifer Encroachment | [5 empty] | 2016-07-16 |  | Ongoing Action
Lewis Well Sage Grouse Habitat Improvement Project | Cave | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Lop & Scatter |  |  | 1000 |  |  | Invasive Species - Conifer Encroachment | Invasive Species - Conifer Encroachment | [5 empty] | 2016-07-15 | 2016-08-15 | Completed
South Spring Valley Anchor Chain/South Spring Valley - Maintenance | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM, NDOW | Treatment - Conifer Lop & Scatter |  |  | 3500 |  |  | Invasive Species - Conifer Encroachment | [6 empty] | 2016-07-16 | 2016-08-16 | Completed
Atlanta Road Sage Grouse Habitat Improvement Project | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM, NDOW | Treatment - Conifer Lop & Scatter | Treatment - Conifer Chaining |  | 6400 |  |  | Invasive Species - Conifer Encroachment | Invasive Species - Conifer Encroachment | [5 empty] | 2015-07-15 |  | Ongoing Action |  |  | 4,200 acres lop and scatter. 2,200 acres chaining
Cave Valley and Lake Valley Watershed Restoration Plan - Removal of Abandoned Power Poles and Lines | Lincoln | NV | BLM - Ely Field Office |  |  | BLM | Powerline Removal |  |  |  | 50 |  | Infrastructure - Powerlines |  | Yes | No | No | No | No | 2014 | 2015 | Completed | Yes |  | Being removed by Lincoln County Telephone System
PROPOSED PROJECTS
Cave Valley and Lake Valley Watershed Restoration Plan - Treatment Unit S-1 (Lincoln Cty Portion Only) | Cave | NV | BLM - Ely Field Office |  | Treatment - Physical | NDOW | Treatment - Conifer Lop & Scatter |  |  | 3400 |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No | 2013-09-01 |  | Implementation in Progress | Yes | Yes | See EA for treatment details and criteria.
Cave Valley and Lake Valley Watershed Restoration Plan - Table Mountain Wildlife Cooridor | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mechanical | Treatment - Conifer Handcutting |  | 200 |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No |  |  | NEPA Completed | No |  | See EA for treatment details and criteria.
Cave Valley and Lake Valley Watershed Restoration Plan - Treatment Unit S-10 | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mechanical | Treatment - Conifer Chemical |  | 5119 |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No |  |  | NEPA Completed | No |  | See EA for treatment details and criteria.
Cave Valley and Lake Valley Watershed Restoration Plan - Treatment Unit S-11 | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mechanical | Treatment - Conifer Chemical |  | 2530 |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No |  |  | NEPA Completed | No |  | See EA for treatment details and criteria.
Cave Valley and Lake Valley Watershed Restoration Plan - Treatment Unit S-12 | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mechanical | Treatment - Conifer Chemical |  | 5468 |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No |  |  | NEPA Completed | No |  | See EA for treatment details and criteria.
Cave Valley and Lake valley Watershed Restoration Plan - Treatment Unit S-13 | Cave | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mechanical | Treatment - Conifer Chemical | Treatment - Sagebrush Mechanical | 2830 |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No |  |  | NEPA Completed | No |  | See EA for treatment details and criteria.
Cave Valley and Lake Valley Watershed Restoration Plan - Treatment Unit S-2 | Cave | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mechanical |  |  | 6781 |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No |  |  | NEPA Completed | No |  | See EA for treatment details and criteria.
Cave Valley and Lake Valley Watershed Restoration Plan - Treatment Unit S-3 | Cave | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mechanical |  |  | 7048 |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No |  |  | NEPA Completed | No |  | See EA for treatment details and criteria.
Cave Valley and Lake Valley Watershed Restoration Plan - Treatment Unit S-5 (Lincoln Cty Portion Only) | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mechanical |  |  | 1457 |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No |  |  | NEPA Completed | No |  | See EA for treatment details and criteria.
Cave Valley and Lake Valley Watershed Restoration Plan - Treatment Unit S-6 | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mechanical |  |  | 3238 |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No |  |  | NEPA Completed | No |  | See EA for treatment details and criteria.
Cave Valley and Lake Valley Watershed Restoration Plan - Treatment Unit S-7 | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mechanical | Treatment - Conifer Chemical |  | 1146 |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No |  |  | NEPA Completed | No |  | See EA for treatment details and criteria.
Cave Valley and Lake Valley Watershed Restoration Plan - Treatment Unit S-8 | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mechanical | Treatment - Conifer Chemical |  | 493 |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No |  |  | NEPA Completed | No |  | See EA for treatment details and criteria.
Cave Valley and Lake Valley Watershed Restoration Plan - Treatment Unit S-9 | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mechanical | Treatment - Conifer Chemical |  | 493 |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No |  |  | NEPA Completed | No |  | See EA for treatment details and criteria.
South Spring Valley and Hamblin Valley Watershed Restoration Plan | Lincoln | NV | BLM - Ely Field Office |  | Treatment - Physical | BLM | Treatment - Conifer Mechanical | Treatment - Conifer Lop & Scatter | Treatment - Seeding | to be determined |  |  | Invasive Species - Conifer Encroachment |  | Yes | No | No | No | No |  |  | NEPA in Progress | No |  | NEPA to be completed FY 2018. See EA for treatment details and criteria.